## Risk Register
Risk ID | Risk Description | Category | Probability | Impact | Mitigation | Owner | Status
R-001 | Data migration errors | Technical | Medium | High | Validate and back up data before migration | Project Manager | Open
R-002 | User resistance to new system | People | High | Medium | Provide training and support | Operations Manager | Open
R-003 | System downtime | Technical | Low | High | Implement backups and monitoring | IT Administrator | Open
R-004 | Incorrect inventory records | Operational | Medium | High | Approval workflow and audits | Warehouse Manager | Open
R-005 | Delayed supplier updates | External | Medium | Medium | Regular supplier communication | Procurement Officer | Open
R-006 | Unauthorized access | Security | Low | High | Role-based access control | System Admin | Open
R-007 | Scope creep | Project | Medium | Medium | Formal change control | Project Manager | Open
R-008 | Missed deadlines | Project | Medium | High | Weekly progress reviews | Project Manager | Open